## Sheet1
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 1 | 2 | 3 | 1 | 1
B | Develop marketing strategy |  | 5 | 10 | 15 | 1 |  |  | 1
C | Design brochure | A | 2 | 3 | 4 |  | 1
D | Develop product prototype
D1 | Requirements analysis | A | 3 | 5 | 7 |  | 1 | 1 | 1 | 1
D2 | Software design | D1 | 10 | 14 | 20 |  | 1 | 1 |  | 1
D3 | System design | D1 | 5 | 10 | 15 |  |  | 1 |  | 1
D4 | Coding | D2, D3 | 15 | 18 | 25 |  | 1 | 1 | 1 | 1
D5 | Write documentation | D4 | 3 | 4 | 6 |  | 1 | 1 | 1 | 1
D6 | Unit testing | D4 | 8 | 10 | 12 |  | 1 | 1 | 1 | 1
D7 | System testing | D6 | 10 | 12 | 15 |  |  | 1 |  | 1
D8 | Package deliverables | D5, D7 | 2 | 3 | 4 | 1
E | Survey potential market | B, C | 5 | 6 | 7 | 1 |  |  | 1
F | Develop pricing plan | D8, E | 2 | 4 | 6 | 1 |  |  | 1
G | Develop implementation plan | A, D8 | 3 | 4 | 5 | 1
H | Write client proposal | F, G | 1 | 2 | 3 | 1
taskID | predecessorTaskIDs | bestCaseHours | worstCaseHours
A |  | 1 | 3
B |  | 5 | 15
C | A | 2 | 4
D1 | A | 3 | 7
D2 | D1 | 10 | 20
D3 | D1 | 5 | 15
D4 | D2, D3 | 15 | 25
D5 | D4 | 3 | 6
D6 | D4 | 8 | 12
D7 | D6 | 10 | 15
D8 | D5, D7 | 2 | 4
E | B, C | 5 | 7
F | D8, E | 2 | 6
G | A, D8 | 3 | 5
H | F, G | 1 | 3

## worstCaseHours
Starter Template
Decision Variables |  | Changing Cells
|  | tA | tB | tC | tD1 | tD2 | tD3 | tD4 | tD5 | tD6 | tD7 | tD8 | tE | tF | tG | tH | z
| worstCaseHours | 3 | 15 | 4 | 7 | 20 | 15 | 25 | 6 | 12 | 15 | 4 | 7 | 6 | 5 | 3
Objective |  | The objective is to minimize z (finish time for the project). I don't think that there really are coeficients... | [15 empty] | Objective Cell
| Profit Coefficients | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | $ -
worstCaseHours
Constraints | Describe product (A-C) | -1 |  | 1 | [13 empty] | 0 | <= | 3
| Describe product (A-D1) | -1 |  |  | 1 | [13 empty] | <= | 3
| Describe product (A-G) | -1 | [12 empty] | 1 |  |  |  | <= | 3
| Develop marketing strategy (B-E) |  | -1 | [9 empty] | 1 |  |  |  |  | 0 | <= | 15
| Design brochure (C-E) |  |  | -1 | [8 empty] | 1 |  |  |  |  | 0 | <= | 4
| Requirements analysis (D1-D2) |  |  |  | -1 | 1 | [11 empty] | 0 | <= | 7
| Requirements analysis (D1-D3) |  |  |  | -1 |  | 1 | [11 empty] | <= | 7
| Software design (D2-D4) |  |  |  |  | -1 |  | 1 | [9 empty] | 0 | <= | 20
| System design (D3-D4) | [5 empty] | -1 | 1 | [9 empty] | 0 | <= | 15
| Coding (D4-D5) | [6 empty] | -1 | 1 | [8 empty] | 0 | <= | 25
| Coding (D4-D6) | [6 empty] | -1 |  | 1 | [8 empty] | <= | 25
| Write documentation (D5-D8) | [7 empty] | -1 |  |  | 1 | [5 empty] | 0 | <= | 6
| Unit testing (D6-D7) | [8 empty] | -1 | 1 | [6 empty] | 0 | <= | 12
| System testing (D7-D8) | [9 empty] | -1 | 1 | [5 empty] | 0 | <= | 15
| Package deliverables (D8-F) | [10 empty] | -1 |  | 1 |  |  |  | 0 | <= | 4
| Package deliverables (D8-G) | [10 empty] | -1 |  |  | 1 |  |  |  | <= | 4
| Survey potential market (E-F) | [11 empty] | -1 | 1 |  |  |  | 0 | <= | 7
| Develop pricing plan (F-H) | [12 empty] | -1 |  | 1 |  | 0 | <= | 6
| Develop implementation plan (G-H) | [13 empty] | -1 | 1 |  | 0 | <= | 5
| Write client proposal (H-z) | [14 empty] | -1 | 1 | 0 | <= | 3

## expectedHours
Starter Template
Decision Variables |  | Changing Cells
|  | tA | tB | tC | tD1 | tD2 | tD3 | tD4 | tD5 | tD6 | tD7 | tD8 | tE | tF | tG | tH | z
| expectedHours | 2 | 10 | 3 | 5 | 14 | 10 | 18 | 4 | 10 | 12 | 3 | 6 | 4 | 4 | 2
Objective |  | The objective is to minimize z (finish time for the project). I don't think that there really are coeficients... | [15 empty] | Objective Cell
| Profit Coefficients | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | $ -
expectedHours
Constraints | Describe product (A-C) | -1 |  | 1 | [13 empty] | 0 | <= | 2
| Describe product (A-D1) | -1 |  |  | 1 | [13 empty] | <= | 2
| Describe product (A-G) | -1 | [12 empty] | 1 |  |  |  | <= | 2
| Develop marketing strategy (B-E) |  | -1 | [9 empty] | 1 |  |  |  |  | 0 | <= | 10
| Design brochure (C-E) |  |  | -1 | [8 empty] | 1 |  |  |  |  | 0 | <= | 3
| Requirements analysis (D1-D2) |  |  |  | -1 | 1 | [11 empty] | 0 | <= | 5
| Requirements analysis (D1-D3) |  |  |  | -1 |  | 1 | [11 empty] | <= | 5
| Software design (D2-D4) |  |  |  |  | -1 |  | 1 | [9 empty] | 0 | <= | 14
| System design (D3-D4) | [5 empty] | -1 | 1 | [9 empty] | 0 | <= | 10
| Coding (D4-D5) | [6 empty] | -1 | 1 | [8 empty] | 0 | <= | 18
| Coding (D4-D6) | [6 empty] | -1 |  | 1 | [8 empty] | <= | 18
| Write documentation (D5-D8) | [7 empty] | -1 |  |  | 1 | [5 empty] | 0 | <= | 4
| Unit testing (D6-D7) | [8 empty] | -1 | 1 | [6 empty] | 0 | <= | 10
| System testing (D7-D8) | [9 empty] | -1 | 1 | [5 empty] | 0 | <= | 12
| Package deliverables (D8-F) | [10 empty] | -1 |  | 1 |  |  |  | 0 | <= | 3
| Package deliverables (D8-G) | [10 empty] | -1 |  |  | 1 |  |  |  | <= | 3
| Survey potential market (E-F) | [11 empty] | -1 | 1 |  |  |  | 0 | <= | 6
| Develop pricing plan (F-H) | [12 empty] | -1 |  | 1 |  | 0 | <= | 4
| Develop implementation plan (G-H) | [13 empty] | -1 | 1 |  | 0 | <= | 4
| Write client proposal (H-z) | [14 empty] | -1 | 1 | 0 | <= | 2

## bestCaseHours
Starter Template
Decision Variables |  | Changing Cells
|  | tA | tB | tC | tD1 | tD2 | tD3 | tD4 | tD5 | tD6 | tD7 | tD8 | tE | tF | tG | tH | z
| bestCaseHours | 1 | 5 | 2 | 3 | 10 | 5 | 15 | 3 | 8 | 10 | 2 | 5 | 2 | 3 | 1
Objective |  | The objective is to minimize z (finish time for the project). I don't think that there really are coeficients... | [15 empty] | Objective Cell
| Profit Coefficients | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | $ -
bestCaseHours
Constraints | Describe product (A-C) | -1 |  | 1 | [13 empty] | 0 | <= | 1
| Describe product (A-D1) | -1 |  |  | 1 | [13 empty] | <= | 1
| Describe product (A-G) | -1 | [12 empty] | 1 |  |  |  | <= | 1
| Develop marketing strategy (B-E) |  | -1 | [9 empty] | 1 |  |  |  |  | 0 | <= | 5
| Design brochure (C-E) |  |  | -1 | [8 empty] | 1 |  |  |  |  | 0 | <= | 2
| Requirements analysis (D1-D2) |  |  |  | -1 | 1 | [11 empty] | 0 | <= | 3
| Requirements analysis (D1-D3) |  |  |  | -1 |  | 1 | [11 empty] | <= | 3
| Software design (D2-D4) |  |  |  |  | -1 |  | 1 | [9 empty] | 0 | <= | 10
| System design (D3-D4) | [5 empty] | -1 | 1 | [9 empty] | 0 | <= | 5
| Coding (D4-D5) | [6 empty] | -1 | 1 | [8 empty] | 0 | <= | 15
| Coding (D4-D6) | [6 empty] | -1 |  | 1 | [8 empty] | <= | 15
| Write documentation (D5-D8) | [7 empty] | -1 |  |  | 1 | [5 empty] | 0 | <= | 3
| Unit testing (D6-D7) | [8 empty] | -1 | 1 | [6 empty] | 0 | <= | 8
| System testing (D7-D8) | [9 empty] | -1 | 1 | [5 empty] | 0 | <= | 10
| Package deliverables (D8-F) | [10 empty] | -1 |  | 1 |  |  |  | 0 | <= | 2
| Package deliverables (D8-G) | [10 empty] | -1 |  |  | 1 |  |  |  | <= | 2
| Survey potential market (E-F) | [11 empty] | -1 | 1 |  |  |  | 0 | <= | 5
| Develop pricing plan (F-H) | [12 empty] | -1 |  | 1 |  | 0 | <= | 2
| Develop implementation plan (G-H) | [13 empty] | -1 | 1 |  | 0 | <= | 3
| Write client proposal (H-z) | [14 empty] | -1 | 1 | 0 | <= | 1